## Risk Log
Identify Risks |  |  | Perform Risk Analysis - Qualitative and Quantitative | [9 empty] | Plan Risk Responses |  |  |  | Monitor and Control Risks
|  |  | Select Type, Risk Category and Impact | [6 empty] | Assessment before Mitigation | [7 empty] | Residual Risk
No | Visibility | Risk Description and Cause | Type | Category | Likelihood | Impact on Project Costs | Impact on Project Timelines | Severity (Project Costs Impact) | Severity (Timelines Impact) | Severity (Calculated) | Sev&Prob | Traffic Light | Mitigation Measure | Contingency Plan | Responsible | Due Date | Status of Mitigation Measure | Likelihood | Severity | Severity&Likelihood | Traffic Light | Comment (Optional)
1 | Internal | Describe the risk; The relationship between cause and effect should be taken into consideration when we identify risks. Describing each risk using three - part statements in the form will help to ensure clarity: “As a result of cause, risk may occur, which would lead to effect.” | Project Environment | Requirements | High (>50) | Medium (10-20%) | High | 2 | 0 | Medium | 32 |  | Describe the mitigation strategy (for reducing the probability of occurrence and/or the impact behind it) | Describe the contingency plan (in case the risk occurs) | Add the person responsible to mitigate the risk | Add the due date, if known | Open | Low (<10) | Low | 11
2 | Internal | “As a result of cause, risk may occur, which would lead to effect.” | Technology | Requirements | Medium (10-50) | Medium (10-20%) | Medium | 2 | 0 | Medium | 22 | [5 empty] | Open | Medium (10-50) | Low | 21
3 | External | “As a result of cause, risk may occur, which would lead to effect.” | Technology | Requirements | High (>50) | Low (<10%) | Low | 1 | 0 | Low | 31 | [5 empty] | Open | Low (<10) | Low | 11

## Graphical Representation
Likelihood |  |  | (before mitigation) |  |  |  | Likelihood |  |  | (after mitigation)
High (>50) | 1 |  | 1 | 0 |  |  | High (>50) | 0 |  | 0 | 0
Medium (10-50) | 0 |  | 1 | 0 |  |  | Medium (10-50) | 1 |  | 0 | 0
Low (<10) | 0 |  | 0 | 0 |  |  | Low (<10) | 2 |  | 0 | 0
| Low |  | Medium | High |  |  |  | Low |  | Medium | High
[5 empty] | Severity | [6 empty] | Severity
|  | Total: | High | [5 empty] | Total: | Low
Remark: Only open, not set to "closed", risks are calculated

## Metadata
Below you will find the definition of most of the values used within the "Risk Log" worksheet. Your project may have a different weight for Small, Medium, High values, thus please feel free to change these values as per your needs, while still maintaining the "Low", "Small", "Medium", "High" strings used in various computations.
Visibility | Spec/Quality/ Outcome (Risk for fulfillment of requirements and/or specifications) | Likelihood | Impact on Project Costs | Status | Residual severity
Internal | Low | Low (<10) | Low (<10%) | Open | Low
External | Medium | Medium (10-50) | Medium (10-20%) | Ongoing | Medium
| High | High (>50) | High (>20%) | Closed | High
Impact on Project costs
Threat Likelihood/Impact | Low (10) | Medium (50) | High (100) | Traffic Light
High (1,0) | 10 * 1,0 = 10 | 50 * 1,0 = 50 | 100 * 1,0 = 100 | Risks that fall within the RED and YELLOW zones will have risk response planning which may include both a risk mitigation and a risk contingency plan.
Medium (0,5) | 10 * 0,5 = 5 | 50 * 0,5 = 25 | 100 * 0,5 = 50
Low (0,1) | 10 * 0,1 = 1 | 50 * 0,1 = 5 | 100 * 0,1 = 10
Risk Types | Risk Types - Examples |  |  | Risk Categories
Project Scope | e.g. no clear documented requirements e.g. development started before sign-off of solution concept Scope creep Missing of expectations/specs Changing requirements Poor project acceptance Wrong time estimation |  |  | Requirements
Project Environment | e.g. tactical and/or strategic focus of project uncertain e.g. clear overall Goals/Objectives of project not defined e.g. project interference to other parallel projects Project targets missed |  |  | Technology
Project Organisation/Roles | E.g. no active top management involvement and no corresponding visibility within the organisation E.g. no active Steering Committee every 4-6 weeks E.g. no clear definition of project roles and responsibilities set up and communicated E.g. no clear structure of decision-making processes and responsibilities set up and communicated E.g. key players from business and IT not involved to contribute to the project (Skill and Time) Project acceptance poor Project targets missed by poor project team |  |  | Communication
Project Management | E.g. Project Management doesn’t have according experience of management of complex projects E.g. no appropriate controlling of cost and time by estimations to complete and actual vs. budget Missing of milestones due to poor planning Budget exceeded |  |  | Human resources
Change Management | E.g. no clear or agreed change request process involving PM, etc. E.g. resistance to change requests on customer site Scope creep Moving target Cost problems /Time and Budget |  |  | Process
Software products | E.g. insufficient vendor involvement for mission critical or early release software projects E.g. insufficient Key user interaction with software for knowledge transfer Missing of user acceptance due to poor software quality High degree of custom development High integration costs (budget and time) |  |  | Budget
Hardware | E.g. unrealistic sizing E.g. strategic Hardware decisions, standards Poor hardware investment decision Costly (budget and time) hardware upgrades |  |  | Schedule
Technology | E.g. new technology for company E.g. insufficient knowledge about technology E.g. Technology/Framework Immaturity |  |  | Quality
Locations/Culture | E.g. distributed development locations E.g. cultural incompatibilities or difficulties due to foreign language E.g. need for presence on customer site in far-away countries High communication efforts and conflicts Poor acceptance High travel cost |  |  | Tools | Reason: Static analysis on code can be used to determine cost of technical debt
Contracts | E.g. unclear acceptance criteria and procedure E.g. contractual liabilities or penalties E.g. Wrong budget estimation E.g. Cost overruns
Quality | QC activity &management immature Poor performance of the application
Client | E.g. difficult client communication E.g. no access to key players from business E.g. unclear political or strategic situation on client site E.g. Lack of stakeholder involvement E.g. Client Team volatility/stakeholder volatility
Project Team | E.g. inexperienced project member/innapropiate team configuration E.g. only few people have critical knowledge E.g. project positions not staffed in time due to lack of appropriate people or people with special expertise assigned to different projects E.g. conflicts in the team E.g. insufficient capacity E.g. Key Employee leaves Project/Company